## BLANK - Risk Reg
PROJECT RISK REGISTER TEMPALTE
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
R1 | 13/05/2026 | Compliance & Accessibility | If one or more accessibiltity features has been missed, then this will effect our project's compliance with WCAG. | 3 | 8 | 24 | The risk is present throughout the project, especially within interface design, and development phases. | Having one person in charge of all UX/UI could lead to a single point of failure. | A robust design system will be created in the planning phase to allow the UX/UI lead to have a guide. As well as a sceduled timeline within GitHub for them to interact with and update us on progress via a repository. | No issues found at this point. | Rachel (Lead UX/UI)
R2 | 13/05/2026 | Scheduling & Time Management | If one or more of the project phase schedules is underestimated, then the project's deployment date could be effected. | 4 | 16 | 64 | This risk is present throughout the entirety of the project, especially within the planning phases. | Having added requirements, and deliverables as the project progresses. Also known as Scope Creep. | By implementing a Change Control Plan this will allow us to evaluate the impacts on the project before integrating the requested change. | No issues found at this point. | Luke (Project Manager)
R3 | 13/05/2026 | Quality Assurance & Testing | If one or more errors go undetected, then the functionality, or even the whole website, could be affected. | 4 | 8 | 32 | This risk is present throughout the entirety of the project, especially within the testing, and post-launch phases. | Having a single person responsible for issue resolution could lead to a single point of failure. | A focus on clear and well structured documentation will help us to follow steps taken by professional throughout their work and find potential oversights. | No issues found at this point. | Janssen (Lead Developer), Michael (Senior Develeper)
R4 | 13/05/2026 | User Experience & User Interface | If one or more user interface elements is poorly designed, then this could reduce usability as well as create a negative user experience. | 3 | 4 | 12 | This risk is present within the interface design phases of the project. | Having one person in charge of all UX/UI could lead to a single point of failure. | By having a usability testing structure that is thorough, we will cover all key user tasks, and interface elements required by representative users. | No issues found at this point. | Rachel (Lead UX/UI)
R5 | 13/05/2026 | Customer Support | If customers are unhappy with our customer support format, then their issues may not be communicated effectively. This could delay fixes as well as create a negative user experience. | 3 | 4 | 12 | This risk is present within the post-launch phases of the project. | Having a reliance on customer issues being recorded through a form format focuses heavily on internal feedback. | Implementing the right automated check system would allow more time to be allocated to additional support channels being offered. | No issues found at this point. | Dan (Customer Support)
R6 | 2026-05-27 | Data Security and Privacy | If user information is not properly protected, then unauthorized acced or data breaches may occur | 2 | 16 | 32 | During development and deployment phases | Weak authentication and database vunerability | Implement encryption, secure authentication and regular security reviews | No issues found at this point. | Janssen (Lead Developer)
R7 | 05/27/26 | Team Communication | If communication between team members is ineffective, then project tasks may be delayed | 3 | 8 | 24 | Whole project lifecycle | Missed meetings or unclear responsibilities | Schedule regular meetings and maintain project documentation on GitHub | No issues found at this point. | Luke (Project Manager)
R8 | 2026-01-06 | Quality Assurance & Testing | If testing does not cover all user scenarios, then defects may be discovered after deployment | 3 | 8 | 24 | Testing phase | Limited test cases | Develop comprehensive test plans and conduct user testing. | No issues found at this point. | Janssen (Lead Developer)
R9 | 2026-06-01 | User Experience & User Interface | If user finds the application difficult to understand, then adaption rate may be lower | 3 | 8 | 24 | Deplyoment and post-launch | Poor onboarding experience | Provide tutorials, guides, and intuitive user interface. | No issues found at this point. | Rachel (Lead UX/UI)
R10 | 2026-01-06 | Quality Assurance & Testing | If the application experiences slow loading times, then users may abandon the platform | 4 | 8 | 32 | Development and testings phases | Large media files and inefficient code | Conduct perfomance testing and optimze application assets and code | No issues found at this point. | Janssen (Lead Developer)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Category titles below to populate the Risk Register Dropdown Menu.
RISK CATEGORY
Compliance & Accessibility
Scheduling & Time Management
Quality Assurance & Testing
User Experience & User Interface
Customer Support
Data Security and Privacy
Team Communication
Category Eight
Category Nine
Category Ten
PROBABILITY
IMPACT